## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name:
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Sujal
Approved By:
SCOPE
Features to be Tested:
1 | Authentication & Authorization Security
2 | Note Management (CRUD) Operations
3 | System Health & Connectivity
4 | UI/API Data Synchronization & Dynamic DOM Updates
TESTING TYPE
Functional Testing | Done
Regression Testing | Done
Integration Testing | Done
UAT | Done
TEST ENVIRONMENT
Environment: | Dev / QA / Staging / Production
Browser/OS: | Chrome
TIMELINE
Start Date: | 2025-06-05
End Date: | 2025-07-05
RESOURCES
QA Lead: | Sujal
QA Resources: | Sujal
Test Data Provider: | Sujal
RISKS & ASSUMPTIONS
Risks: | All locators are stable
Assumptions: | The major functions and requriements are defined

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | Access Not+B2:B16es Url Without Login | Verify that a user cannot access the notes page directly via URL without logging in. | User is not authenticated/logged out.
SC-002 | Access Profile Url Without Login | Verify that a user cannot access the profile page directly via URL without logging in. | User is not authenticated/logged out.
SC-003 | Access Protected Api Without Authentication | Verify that protected API endpoints return an unauthorized error when accessed without a token. | No valid API authentication token is provided.
SC-004 | Create Note Api | Verify that a new note can be successfully created using the API endpoint. | Valid API authentication token is available.
SC-005 | Delete Note Api | Verify that an existing note can be deleted using the API endpoint. | Note exists; valid API token is available.
SC-006 | Get All Notes Api | Verify that a user's list of notes can be successfully retrieved via the GET API. | Valid API authentication token is available.
SC-007 | Get Notes Without Authentication | Verify that the GET notes API endpoint rejects requests lacking valid authentication. | No valid API authentication token is provided.
SC-008 | Health Check Api | Verify that the API health check endpoint responds successfully, indicating the service is up. | API server is running and accessible.
SC-009 | Login Api | Verify that a user can successfully authenticate and receive a token via the login API. | Registered user account exists.
SC-010 | Login Api Invalid Password | Verify that the login API rejects authentication attempts with an incorrect password. | Registered user account exists.
SC-011 | Register With Existing Email | Verify that the API prevents registration of a new account using an email that is already in use. | User email already exists in the database.
SC-012 | Validate Api Deletion Reflected In Ui | Verify that when a note is deleted via the API, it correctly disappears from the frontend UI. | User is logged into UI; note exists in the account.
SC-013 | Validate Ui To Api Note Consistency | Verify that a note created through the UI perfectly matches the data returned by the API. | User is logged into UI.
SC-014 | Login Invalid Credentials | Verify that the UI displays an appropriate error when attempting to log in with wrong credentials. | Application is loaded on the login screen.
SC-015 | Valid Login | Verify that a user can successfully log into the UI with valid credentials. | Registered user account exists.
SC-016 | Create Note Empty Fields | Verify that the UI displays validation errors when attempting to save a note without required fields. | User is logged and and Note modal is open.
SC-017 | Create Note Valid | Verify that a user can successfully create a new note with valid data through the UI. | User is logged in.
SC-018 | Delete Existing Note | Verify that a user can successfully delete an existing note through the UI. | User is logged in at least one note exists.
SC-019 | Edit Existing Note | Verify that a user can successfully modify and save changes to an existing note in the UI. | User is logged in at least one note exists.
SC-020 | Mark Note As Completed | Verify that a user can successfully toggle a note's status to "completed" in the UI. | User is logged in an incomplete note exists.
SC-021 | Launch App | Verify that the frontend web application loads correctly without critical errors. | Web server is running.

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-001 | SC-001 | Access Notes Url Without Login | User is not logged in | 1. Open browser 2. Enter /notes URL directly 3. Press Enter | User is redirected to the login page | High | Pass
TC-002 | SC-002 | Access Profile Url Without Login | User is not logged in | 1. Open browser 2. Enter /profile URL directly 3. Press Enter | User is redirected to the login page | High | Pass
TC-003 | SC-003 | Access Protected Api Without Authentication | No valid API token available | 1. Send API request to a protected endpoint without an auth token | API returns a 401 Unauthorized error | High | Pass
TC-004 | SC-004 | Create Note Api | Valid API auth token available | 1. Send POST request to /notes with note payload | API returns 201 Created and note details | High | Pass
TC-005 | SC-005 | Delete Note Api | Note exists, valid API token | 1. Send DELETE request to /notes/{id} | API returns success status (200/204) | High | Pass
TC-006 | SC-006 | Get All Notes Api | Valid API auth token available | 1. Send GET request to /notes | API returns 200 OK and user's list of notes | High | Pass
TC-007 | SC-007 | Get Notes Without Authentication | No valid API token available | 1. Send GET request to /notes without token | API returns a 401 Unauthorized error | High | Pass
TC-008 | SC-008 | Health Check Api | API server is running | 1. Send GET request to health-check endpoint | API returns 200 OK indicating service is up | Medium | Pass
TC-009 | SC-009 | Login Api | Registered user account exists | 1. Send POST to /login with valid credentials | API returns 200 OK and authentication token | High | Pass
TC-010 | SC-010 | Login Api Invalid Password | Registered user account exists | 1. Send POST to /login with wrong password | API returns 401 Unauthorized | High | Pass
TC-011 | SC-011 | Register With Existing Email | User email already exists | 1. Send POST to /register with existing email | API returns 409 Conflict / error message | Medium | Pass
TC-012 | SC-012 | Validate Api Deletion Reflected In Ui | Note exists, user logged into UI | 1. Delete note via API 2. Refresh frontend UI | Deleted note is no longer visible in UI | High | Pass
TC-013 | SC-013 | Validate Ui To Api Note Consistency | User logged into UI | 1. Create note in UI 2. Call GET notes API | UI note data perfectly matches API response | High | Pass
TC-014 | SC-014 | Login Invalid Credentials | Application is on login screen | 1. Enter valid email 2. Enter wrong password 3. Click Login | UI displays appropriate error message | High | Pass
TC-015 | SC-015 | Valid Login | Registered user account exists | 1. Enter valid email and password 2. Click Login | User is successfully redirected to notes dashboard | High | Pass
TC-016 | SC-016 | Create Note Empty Fields | Add Note modal is open in UI | 1. Leave mandatory fields empty 2. Click Save | UI displays required field validation errors | High | Pass
TC-017 | SC-017 | Create Note Valid | User logged into application | 1. Click Add Note 2. Enter valid details 3. Click Save | Note is successfully created and displayed in UI | High | Pass
TC-018 | SC-018 | Delete Existing Note | At least one note exists in UI | 1. Click Delete on a note 2. Confirm in popup | Note is successfully removed from the UI | High | Pass
TC-019 | SC-019 | Edit Existing Note | At least one note exists in UI | 1. Click Edit on a note 2. Modify text 3. Click Save | Updated text correctly reflects on the note | High | Pass
TC-020 | SC-020 | Mark Note As Completed | An incomplete note exists in UI | 1. Click completion checkbox on the note | Note status toggles to completed visually | Medium | Pass
TC-021 | SC-021 | Launch App | Web server is running | 1. Navigate to frontend base application URL | Application UI loads without critical errors | High | Pass

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid Registered User | Email: testuser2005@gmail.com, Password: qwerty | Valid login scenarios
TD-002 | Invalid Login User | Email: testuser2005@gmail.com, Password: qwerty | Negative login validation
TD-003 | New User Registration | Name: Test User, Email: testuser2005@gmail.com, Password: qwerty | User registration testing
TD-004 | Duplicate Registration User | Email: testuser2005@gmail.com | Duplicate user registration validation
TD-005 | Empty Registration Data | Name: "", Email: testuser2005@gmail.com, Password: qwerty | Mandatory field validation
TD-006 | Valid Note Data | Title: CAPSTIME 2026-05-07 00:02:54, Description: project, Category: Home | Valid note creation
TD-007 | Work Category Note | Title: CAPSTIME 2026-05-07 00:02:54, Description: project, Category: Work | Category filtering validation
TD-008 | Personal Category Note | Title: CAPSTIME 2026-05-07 00:02:54, Description: project, Category: Personal | Personal category testing
TD-009 | Empty Note Data | Title: CAPSTIME 2026-05-07 00:02:54, Description: project | Note validation testing
TD-010 | Long Text Note Data | Title: CAPSTIME 2026-05-07 00:02:54, Description: project | Boundary value testing
TD-011 | Special Character Data | Title: CAPSTIME 2026-05-07 00:02:54, Description: project | Input handling validation
TD-012 | Search Keyword Data | Keyword: kitchen | Search functionality testing
TD-013 | Updated Note Data | Updated Title: CAPSTIME 2026-05-07 00:02:54, Updated Description: project | Note edit validation
TD-014 | Completed Note Data | Checkbox: Checked | Note completion testing
TD-015 | Valid API Credentials | Email: testuser2005@gmail.com, Password: qwerty | API authentication testing
TD-016 | Invalid API Token | Token: invalid_token_123 | Unauthorized API access testing
TD-017 | Valid API Note Payload | { "title":"CAPSTIME 2026-05-07 00:02:54", "description":"project", "category":"Work" } | API note creation
TD-018 | Invalid API Payload | { "title":"CAPSTIME 2026-05-07 00:02:54", "description":"project" } | API validation testing
TD-019 | Existing Note ID | Note ID: Existing valid note ID from GET /notes | API delete/update testing
TD-020 | Invalid Note ID | Note ID: invalid12345 | Negative API delete testing
TD-021 | Health Check Endpoint | Endpoint: /health-check | API health validation
TD-022 | Profile Update Data | Full Name: Tyson QA, Phone: 9876543210, Company: Capgemini | Profile update testing
TD-023 | Unauthorized URL Data | URL: /notes/app/profile | Unauthorized direct URL access validation
TD-024 | Response Time Benchmark | Expected Response Time: < 2 seconds | API performance validation
TD-025 | Logout Session Data | Active logged-in session | Logout and session validation

## 5. Test Execution
x | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Register user with valid details | QA-Sujal | 2026-05-06 | Pass |  | User registered successfully
TC-002 | Cycle-1 | Register with empty mandatory fields | QA-Sujal | 2026-05-06 | Pass |  | Validation messages displayed correctly
TC-003 | Cycle-1 | Login with valid credentials | QA-Sujal | 2026-05-06 | Pass |  | User redirected to Notes dashboard
TC-004 | Cycle-1 | Login with invalid credentials | QA-Sujal | 2026-05-06 | Pass |  | Proper error message displayed
TC-005 | Cycle-1 | Create note with valid details | QA-Sujal | 2026-05-06 | Pass |  | Note created successfully
TC-006 | Cycle-1 | Create note with empty title and description | QA-Sujal | 2026-05-06 | Pass |  | Mandatory field validations working correctly
TC-007 | Cycle-1 | Verify instant note rendering | QA-Sujal | 2026-05-06 | Pass |  | Note displayed instantly without refresh
TC-008 | Cycle-1 | Mark note as completed | QA-Sujal | 2026-05-06 | Pass |  | Completion checkbox updated status successfully
TC-009 | Cycle-1 | Validate completed notes counter | QA-Sujal | 2026-05-06 | Pass |  | Completed notes count updated dynamically
TC-010 | Cycle-1 | Filter notes by category | QA-Sujal | 2026-05-06 | Pass |  | Category filtering working correctly
TC-011 | Cycle-1 | Search notes using keyword | QA-Sujal | 2026-05-06 | Pass |  | Search results displayed correctly
TC-012 | Cycle-1 | Edit existing note | QA-Sujal | 2026-05-06 | Pass | DEF-001 | Updated description not reflected immediately
TC-013 | Cycle-1 | Delete note using confirmation popup | QA-Sujal | 2026-05-06 | Pass |  | Note deleted successfully
TC-014 | Cycle-1 | Cancel note deletion | QA-Sujal | 2026-05-06 | Pass |  | Note remained unchanged after cancellation
TC-015 | Cycle-1 | Logout from application | QA-Sujal | 2026-05-06 | Pass |  | User logged out successfully
TC-016 | Cycle-1 | Update profile information | QA-Sujal | 2026-05-06 | Pass |  | Profile details updated successfully
TC-017 | Cycle-1 | Login using API endpoint | QA-Sujal | 2026-05-06 | Pass |  | Authentication token generated successfully
TC-018 | Cycle-1 | Register user using API | QA-Sujal | 2026-05-06 | Pass |  | API user registration successful
TC-019 | Cycle-1 | Retrieve notes using GET API | QA-Sujal | 2026-05-06 | Pass |  | Notes retrieved successfully
TC-020 | Cycle-1 | Create note using API | QA-Sujal | 2026-05-06 | Pass |  | Note created successfully via API
TC-021 | Cycle-1 | Delete note using API | QA-Sujal | 2026-05-06 | Pass |  | Note deleted successfully via API
TC-022 | Cycle-1 | Validate UI to API note consistency | QA-Sujal | 2026-05-06 | Pass |  | UI and API note data matched correctly
TC-023 | Cycle-1 | Validate API deletion reflected in UI | QA-Sujal | 2026-05-06 | Pass |  | Deleted note removed from UI after refresh
TC-024 | Cycle-1 | Access API without token | QA-Sujal | 2026-05-06 | Pass |  | Unauthorized access blocked correctly
TC-025 | Cycle-1 | Send invalid payload to API | QA-Sujal | 2026-05-06 | Pass |  | Proper validation error returned
TC-026 | Cycle-1 | Validate API response time | QA-Sujal | 2026-05-06 | Pass |  | API response received within expected threshold
TC-027 | Cycle-1 | Verify health-check API | QA-Sujal | 2026-05-06 | Pass |  | API service status returned successfully
TC-028 | Cycle-1 | Register with existing email | QA-Sujal | 2026-05-06 | Pass |  | Duplicate registration prevented successfully
TC-029 | Cycle-1 | Access protected pages without login | QA-Sujal | 2026-05-06 | Pass |  | Unauthorized user redirected to login page
TC-030 | Cycle-1 | Access protected API without authentication | QA-Sujal | 2026-05-06 | Pass |  | Unauthorized API access denied correctly

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
REQ-001 | TC-014, TC-015 | User should be able to login to the application with valid/invalid credentials. | Covered | Complete
REQ-002 | TC-016, TC-017 | User should be able to create notes through the UI with validation. | Covered | Complete
REQ-003 | TC-019 | User should be able to edit existing notes in the UI. | Covered | Complete
REQ-004 | TC-018 | User should be able to delete notes through the UI. | Covered | Complete
REQ-005 | TC-020 | User should be able to mark notes as completed. | Covered | Complete
REQ-006 | TC-001, TC-002 | System should prevent unauthorized direct URL access to protected pages. | Covered | Complete
REQ-007 | TC-009, TC-010 | API should authenticate users and handle invalid passwords correctly. | Covered | Complete
REQ-008 | TC-011 | System should prevent API registration with an existing email. | Covered | Complete
REQ-009 | TC-006, TC-007 | API should allow note retrieval and reject unauthenticated requests. | Covered | Complete
REQ-010 | TC-004 | API should allow for note creation via endpoint. | Covered | Complete
REQ-011 | TC-005 | API should allow for note deletion via endpoint. | Covered | Complete
REQ-012 | TC-003 | API should reject access to protected endpoints without a token. | Covered | Complete
REQ-013 | TC-013 | UI-created notes should match data returned by the API. | Covered | Complete
REQ-014 | TC-012 | API-deleted notes should disappear from the UI. | Covered | Complete
REQ-015 | TC-008 | API should provide a working health-check endpoint. | Covered | Complete
REQ-016 | TC-021 | The frontend application should launch and load successfully. | Covered | Complete

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-012 | No refrence Identifier | Refresh in dom and dynamic change in created locator no refrence to a particular note | low | low | completed | sujal | 2025-06-05 | 0

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name:
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By:
EXECUTION SUMMARY
Total Test Cases: | 21
Test Cases Executed: | 21
Test Cases Passed: | 21
Test Cases Failed: | 0
Pass Percentage: | 100
DEFECT SUMMARY
Total Defects: | 1
Critical Defects: | 0
High Defects: | 0
Medium Defects: | 0
Low Defects: | 0
Open Defects: | 0
Closed Defects: | 1
CONCLUSION
Testing Status: | Completed
Release Readiness: | Minor changes
Overall Recommendation: | Production
REMARKS | Ads ui element is not consistent